## Sheet1
Epic
Name | Description | Parent Initiative | Owner | Planning Quarters | Primary Program | Secondary Program
PY4.0 ¦¦ DESIGN AND BUILD | PY4.0 ¦¦ DESIGN AND BUILD | HUM-Payroll | MStewart6@slb.com | PQ-2022.1, PQ-2022.2, PQ-2022.3, PQ-2022.4 | SAP H2R
PY4.0 ¦¦ CHANGE IMPACT ASSESSMENT | PY4.0 ¦¦ CHANGE IMPACT ASSESSMENT | HUM-Payroll | HSalcedo@slb.com | PQ-2022-2, PQ-2022.3 | SAP H2R
PY4.0 ¦¦ COMMUNICATION | PY4.0 ¦¦ COMMUNICATION | HUM-Payroll | HSalcedo@slb.com | PQ-2022.1, PQ-2022.2, PQ-2022.3, PQ-2022.4 | SAP H2R
PY4.0 ¦¦ CUTOVER | PY4.0 ¦¦ CUTOVER | HUM-Payroll | SKendhe@slb.com | PQ-2022.2, PQ-2022.3, PQ-2022.4 ,PQ-2023.1, | SAP H2R
PY4.0 ¦¦ DATA CONVERSION | PY4.0 ¦¦ DATA CONVERSION | HUM-Payroll | SKendhe@slb.com | PQ-2022.1, PQ-2022.2, PQ-2022.3, PQ-2022.4 | SAP H2R
PY4.0 ¦¦ DATA READINESS | PY4.0 ¦¦ DATA READINESS | HUM-Payroll | MStewart6@slb.com | PQ-2022.1, PQ-2022.2, PQ-2022.3, PQ-2022.4 | SAP H2R
PY4.0 ¦¦ END USER TRAINING | PY4.0 ¦¦ END USER TRAINING | HUM-Payroll | HSalcedo@slb.com | PQ-2022.2, PQ-2022.3, PQ-2022.4 | SAP H2R
PY4.0 ¦¦ GO-LIVE MILESTONE | PY4.0 ¦¦ GO-LIVE MILESTONE | HUM-Payroll | JBakshi@slb.com | PQ-2023.1, | SAP H2R
PY4.0 ¦¦ GOVERNANCE MODEL | PY4.0 ¦¦ GOVERNANCE MODEL | HUM-Payroll | AKulkarni11@slb.com/yileng@slb.com | PQ-2022.1, PQ-2022.4 | SAP H2R
PY4.0 ¦¦ HAND-OFF TO SUSTAINING | PY4.0 ¦¦ HAND-OFF TO SUSTAINING | HUM-Payroll | HSalcedo@slb.com | PQ-2023.1, | SAP H2R
PY4.0 ¦¦ INTEGRATION TESTING | PY4.0 ¦¦ INTEGRATION TESTING | HUM-Payroll | RShinde8@slb.com | PQ-2022.3, PQ-2022.4 | SAP H2R
PY4.0 ¦¦ LEADERSHIP ACTIONS AND SIGN-OFF | PY4.0 ¦¦ LEADERSHIP ACTIONS AND SIGN-OFF | HUM-Payroll | AKulkarni11@slb.com/yileng@slb.com | PQ-2022.1, | SAP H2R
PY4.0 ¦¦ ORGANIZATIONAL READINESS | PY4.0 ¦¦ ORGANIZATIONAL READINESS | HUM-Payroll | AKulkarni11@slb.com/yileng@slb.com | PQ-2022.1, PQ-2022.2, | SAP H2R
PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT | HUM-Payroll | MStewart6@slb.com | PQ-2022.3, PQ-2023.2 | SAP H2R
PY4.0 ¦¦ PROJECT PLAN | PY4.0 ¦¦ PROJECT PLAN | HUM-Payroll | JBakshi@slb.com | PQ-2022.1, | SAP H2R
PY4.0 ¦¦ RESOURCE ASSIGNMENT | PY4.0 ¦¦ RESOURCE ASSIGNMENT | HUM-Payroll | AKulkarni11@slb.com/yileng@slb.com | PQ-2021.4, PQ-2022.1, | SAP H2R
PY4.0 ¦¦ RISK MANAGEMENT | PY4.0 ¦¦ RISK MANAGEMENT | HUM-Payroll | HSalcedo@slb.com | PQ-2022.1, PQ-2023.1 | SAP H2R
PY4.0 ¦¦ SECURITY READINESS | PY4.0 ¦¦ SECURITY READINESS | HUM-Payroll | KPande@slb.com | PQ-2022.1, PQ-2022.2, PQ-2022.3, PQ-2022.4 | SAP H2R
PY4.0 ¦¦ SOLUTION READINESS | PY4.0 ¦¦ SOLUTION READINESS | HUM-Payroll | MStewart6@slb.com | PQ-2022.1, PQ-2022.2, PQ-2022.3, | SAP H2R
PY4.0 ¦¦ SYSTEM INFRASTRUCTURE | PY4.0 ¦¦ SYSTEM INFRASTRUCTURE | HUM-Payroll | SDas23@slb.com | PQ-2022.3, PQ-2022.4 | SAP H2R
PY4.0 ¦¦ LEADERSHIP ENGAGEMENT | PY4.0 ¦¦ LEADERSHIP ENGAGEMENT | HUM-Payroll | AKulkarni11@slb.com/yileng@slb.com | PQ-2022.1 | SAP H2R
PY4.0 ¦¦ PROJECT VISION AND GOALS | PY4.0 ¦¦ PROJECT VISION AND GOALS | HUM-Payroll | AKulkarni11@slb.com/yileng@slb.com | PQ-2022.1 | SAP H2R
PY4.0 ¦¦ STAKEHOLDER MANAGEMENT | PY4.0 ¦¦ STAKEHOLDER MANAGEMENT | HUM-Payroll | HSalcedo@slb.com | PQ-2022.1, PQ-2022.2, PQ-2022.3, PQ-2022.4 | SAP H2R

## Sheet2
Features
Name | Description | Parent Epic | Planning Quarter | Owner | Target Start | Target Finish | Primary Program | Product | Tag
PY4.0 - MY ¦¦ DESIGN AND BUILD - Baseline Configuration | PY4.0 – MY ¦¦ DESIGN AND BUILD - Baseline Configuration | PY4.0 ¦¦ DESIGN AND BUILD | PQ-2022.2 | MStewart6@slb.com | 2022-01-27 | 2022-06-29 | SAP H2R | ITT SAP | MY
PY4.0 - MY ¦¦ DESIGN AND BUILD - Heritage/Legacy System Gap Build and FUT | PY4.0 – MY ¦¦ DESIGN AND BUILD - Heritage/Legacy System Gap Build and FUT | PY4.0 ¦¦ DESIGN AND BUILD | PQ-2022.2 | MStewart6@slb.com | 2022-01-27 | 2022-06-29 | SAP H2R | ITT SAP | MY
PY4.0 - MY ¦¦ DESIGN AND BUILD - AWDs, Change Impacts, BPPs, New BR's | PY4.0 – MY ¦¦ DESIGN AND BUILD - AWDs, Change Impacts, BPPs, New BR's | PY4.0 ¦¦ DESIGN AND BUILD | PQ-2022.2 | MStewart6@slb.com | 2022-02-24 | 2022-06-15 | SAP H2R | ITT SAP | MY
PY4.0 - MY ¦¦ DESIGN AND BUILD - Localization Configuration | PY4.0 – MY ¦¦ DESIGN AND BUILD - Baseline Configuration | PY4.0 ¦¦ DESIGN AND BUILD | PQ-2022.2 | MStewart6@slb.com | 2022-01-27 | 2022-06-29 | SAP H2R | ITT SAP | MY
PY4.0 - MY ¦¦ DESIGN AND BUILD - Global Template Changes | PY4.0 – MY ¦¦ DESIGN AND BUILD - Global Template Changes | PY4.0 ¦¦ DESIGN AND BUILD | PQ-2022.2 | MStewart6@slb.com | 2022-01-27 | 2022-06-29 | SAP H2R | ITT SAP | MY
PY4.0 - MY ¦¦ DESIGN AND BUILD -Solution FUT | PY4.0 – MY ¦¦ DESIGN AND BUILD -Solution FUT | PY4.0 ¦¦ DESIGN AND BUILD | PQ-2022.2 | MStewart6@slb.com | 2022-01-27 | 2022-06-29 | SAP H2R | ITT SAP | MY
PY4.0 - MY ¦¦ DESIGN AND BUILD - WRI_EF Design, Build and TUT/FUT | PY4.0 – MY ¦¦ DESIGN AND BUILD - WRI_EF Design, Build and TUT/FUT | PY4.0 ¦¦ DESIGN AND BUILD | PQ-2022.2 | MStewart6@slb.com | 2022-01-27 | 2022-06-29 | SAP H2R | ITT SAP | MY
PY4.0 - MY ¦¦ DESIGN AND BUILD - Change Requests post Scope Freeze and Design Freeze | PY4.0 – MY ¦¦ DESIGN AND BUILD - Change Requests post Scope Freeze and Design Freeze | PY4.0 ¦¦ DESIGN AND BUILD | PQ-2022.4 | MStewart6@slb.com | 2022-08-25 | 2022-11-02 | SAP H2R | ITT SAP | MY
PY4.0 ¦¦ CUTOVER - Cutover Strategy Documents | PY4.0 ¦¦ CUTOVER - Cutover Strategy Documents | PY4.0 ¦¦ CUTOVER | PQ-2022.2 | SKendhe@slb.com | 2022-04-07 | 2022-06-01 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - Update Cutover Strategy Documents with Feedback | PY4.0 ¦¦ CUTOVER - Update Cutover Strategy Documents with Feedback | PY4.0 ¦¦ CUTOVER | PQ-2022.3 | SKendhe@slb.com | 2022-06-02 | 2022-08-10 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - Develop Cutover Plan | PY4.0 ¦¦ CUTOVER - Develop Cutover Plan | PY4.0 ¦¦ CUTOVER | PQ-2022.2 | SKendhe@slb.com | 2022-05-05 | 2022-06-15 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - Cutover DC1 Refine Plan | PY4.0 ¦¦ CUTOVER - Cutover DC1 Refine Plan | PY4.0 ¦¦ CUTOVER | PQ-2022.2 | SKendhe@slb.com | 2022-06-16 | 2022-06-29 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - Cutover DC2 Refine Plan | PY4.0 ¦¦ CUTOVER - Cutover DC2 Refine Plan | PY4.0 ¦¦ CUTOVER | PQ-2022.3 | SKendhe@slb.com | 2022-07-28 | 2022-08-10 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - Cutover DC3 Refine Plan | PY4.0 ¦¦ CUTOVER - Cutover DC3 Refine Plan | PY4.0 ¦¦ CUTOVER | PQ-2022.3 | SKendhe@slb.com | 2022-09-08 | 2022-09-21 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - Cutover Finalize Plan for Production | PY4.0 ¦¦ CUTOVER - Cutover Finalize Plan for Production | PY4.0 ¦¦ CUTOVER | PQ-2022.4 | SKendhe@slb.com | 2022-11-03 | 2022-11-16 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - Production Cutover Prep | PY4.0 ¦¦ CUTOVER - Production Cutover Prep | PY4.0 ¦¦ CUTOVER | PQ-2022.4 | SKendhe@slb.com | 2022-12-01 | 2022-12-14 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - Production Cutover Execute | PY4.0 ¦¦ CUTOVER - Production Cutover Execute | PY4.0 ¦¦ CUTOVER | PQ-2022.4 | SKendhe@slb.com | 2022-12-01 | 2022-12-14 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - Production Cutover Black Out Loads | PY4.0 ¦¦ CUTOVER - Production Cutover Black Out Loads | PY4.0 ¦¦ CUTOVER | PQ-2023.1 | SKendhe@slb.com | 2022-12-29 | 2023-01-03 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - Production Cutover Loads | PY4.0 ¦¦ CUTOVER - Production Cutover Loads | PY4.0 ¦¦ CUTOVER | PQ-2022.4 | SKendhe@slb.com | 2022-12-15 | 2022-12-28 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - Production Cutover Lessons Learned capture | PY4.0 ¦¦ CUTOVER - Production Cutover Lessons Learned capture | PY4.0 ¦¦ CUTOVER | PQ-2023.1 | SKendhe@slb.com | 2022-12-29 | 2023-01-11 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA READINESS - Data Prep and Scorecards | PY4.0 ¦¦ DATA READINESS - Data Prep and Scorecards | PY4.0 ¦¦ DATA READINESS | PQ-2022.1 | JBakshi@slb.com | 2022-02-10 | 2022-03-23 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA READINESS - Data Readiness Coaching | PY4.0 ¦¦ DATA READINESS - Data Readiness Coaching | PY4.0 ¦¦ DATA READINESS | PQ-2022.2 | HSalcedo@slb.com | 2022-03-24 | 2022-05-18 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - Dry Run Prep 1 | PY4.0 ¦¦ INTEGRATION TESTING - Dry Run Prep 1 | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.3 | RShinde8@slb.com | 2022-05-05 | 2022-06-29 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - Dry Run Execute 1 | PY4.0 ¦¦ INTEGRATION TESTING - Dry Run Execute 1 | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-06-30 | 2022-11-30 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT1 Prep | PY4.0 ¦¦ INTEGRATION TESTING - SIT1 Prep | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-06-16 | 2022-11-30 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT1 Execute | PY4.0 ¦¦ INTEGRATION TESTING - SIT1 Execute | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.3 | RShinde8@slb.com | 2022-07-28 | 2022-08-24 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT1 Lessons Learned capture | PY4.0 ¦¦ INTEGRATION TESTING - SIT1 Lessons Learned capture | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.3 | RShinde8@slb.com | 2022-08-25 | 2022-09-07 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING -RT1 Prep | PY4.0 ¦¦ INTEGRATION TESTING -RT1 Prep | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.3 | RShinde8@slb.com | 2022-07-14 | 2022-07-27 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - RT1 Execute | PY4.0 ¦¦ INTEGRATION TESTING - RT1 Execute | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.3 | RShinde8@slb.com | 2022-07-28 | 2022-08-24 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - Dry Run Prep 2 | PY4.0 ¦¦ INTEGRATION TESTING - Dry Run Prep 2 | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-09-22 | 2022-10-05 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - Dry Run Execute 2 | PY4.0 ¦¦ INTEGRATION TESTING - Dry Run Execute 2 | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-10-13 | 2022-10-26 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT2 Prep | PY4.0 ¦¦ INTEGRATION TESTING - SIT2 Prep | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.3 | RShinde8@slb.com | 2022-09-08 | 2022-09-21 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT2 Execute | PY4.0 ¦¦ INTEGRATION TESTING - SIT2 Execute | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-09-29 | 2022-10-19 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT2 Lessons Learned capture | PY4.0 ¦¦ INTEGRATION TESTING - SIT2 Lessons Learned capture | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-10-20 | 2022-11-02 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - RT2 Prep | PY4.0 ¦¦ INTEGRATION TESTING - RT2 Prep | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.3 | RShinde8@slb.com | 2022-09-08 | 2022-09-21 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - RT2 Execute | PY4.0 ¦¦ INTEGRATION TESTING - RT2 Execute | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-09-29 | 2022-10-19 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - Dry Run Prep 3 | PY4.0 ¦¦ INTEGRATION TESTING - Dry Run Prep 3 | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-11-17 | 2022-11-30 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING -Dry Run Execute 3 | PY4.0 ¦¦ INTEGRATION TESTING - Dry Run Execute 3 | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-12-01 | 2022-12-14 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT3 Prep | PY4.0 ¦¦ INTEGRATION TESTING - SIT3 Prep | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-10-31 | 2022-11-25 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT3 Execute | PY4.0 ¦¦ INTEGRATION TESTING - SIT3 Execute | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-11-17 | 2022-12-08 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT3 Lessons Learned capture | PY4.0 ¦¦ INTEGRATION TESTING - SIT3 Lessons Learned capture | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-12-15 | 2022-12-28 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - Solution Assurance Prep | PY4.0 ¦¦ INTEGRATION TESTING - Solution Assurance Prep | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-12-01 | 2022-12-28 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - RT3 Prep | PY4.0 ¦¦ INTEGRATION TESTING - RT3 Prep | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-10-31 | 2022-11-25 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - RT3 Execute | PY4.0 ¦¦ INTEGRATION TESTING - RT3 Execute | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-11-17 | 2022-12-08 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CHANGE IMPACT ASSESSMENT - Validate Change Impacts and define change plan | PY4.0 ¦¦ CHANGE IMPACT ASSESSMENT - Validate Change Impacts and define change plan | PY4.0 ¦¦ CHANGE IMPACT ASSESSMENT | PQ-2022.3 | HSalcedo@slb.com | 2022-05-19 | 2022-07-27 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CHANGE IMPACT ASSESSMENT - Update What's Changing document (Key Changes/Building Blocks) | PY4.0 ¦¦ CHANGE IMPACT ASSESSMENT - Update What's Changing document (Key Changes/Building Blocks) | PY4.0 ¦¦ CHANGE IMPACT ASSESSMENT | PQ-2022.2 | HSalcedo@slb.com | 2022-04-21 | 2022-06-29 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ COMMUNICATION - Communicate Release Vision, Value & Scorecards | PY4.0 ¦¦ COMMUNICATION - Communicate Release Vision, Value & Scorecards | PY4.0 ¦¦ COMMUNICATION | PQ-2022.2 | HSalcedo@slb.com | 2022-02-10 | 2022-04-20 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ COMMUNICATION - Communicate WC Key Changes | PY4.0 ¦¦ COMMUNICATION - Communicate WC Key Changes | PY4.0 ¦¦ COMMUNICATION | PQ-2022.3 | HSalcedo@slb.com | 2022-02-10 | 2022-06-01 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ COMMUNICATION - Communicate Cutover Plan and Blackout requirements | PY4.0 ¦¦ COMMUNICATION - Communicate Cutover Plan and Blackout requirements | PY4.0 ¦¦ COMMUNICATION | PQ-2022.4 | HSalcedo@slb.com | 2022-10-06 | 2022-12-14 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ COMMUNICATION - Communicate PDS Plan to Stakeholders & End Users | PY4.0 ¦¦ COMMUNICATION - Communicate PDS Plan to Stakeholders & End Users | PY4.0 ¦¦ COMMUNICATION | PQ-2022.4 | HSalcedo@slb.com | 2022-10-31 | 2022-12-09 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ COMMUNICATION - Communicate Training Schedule to End Users | PY4.0 ¦¦ COMMUNICATION - Communicate Training Schedule to End Users | PY4.0 ¦¦ COMMUNICATION | PQ-2022.4 | HSalcedo@slb.com | 2022-08-11 | 2022-10-05 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ COMMUNICATION - Communicate Cutover Plan and Blackout requirements | PY4.0 ¦¦ COMMUNICATION - Communicate Cutover Plan and Blackout requirements | PY4.0 ¦¦ COMMUNICATION | PQ-2022.4 | HSalcedo@slb.com | 2022-10-20 | 2022-12-14 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - Post-Go-Live Loads | PY4.0 ¦¦ DATA CONVERSION - Post-Go-Live Loads | PY4.0 ¦¦ DATA CONVERSION | PQ-2023.1 | SKendhe@slb.com | 2023-01-12 | 2023-01-25 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - Conversion Build and TUT | PY4.0 ¦¦ DATA CONVERSION - Conversion Build and TUT | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.2 | SKendhe@slb.com | 2022-01-27 | 2022-06-15 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC1 Prep | PY4.0 ¦¦ DATA CONVERSION - DC1 Prep | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.2 | SKendhe@slb.com | 2022-06-16 | 2022-06-29 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC1 Execute | PY4.0 ¦¦ DATA CONVERSION - DC1 Execute | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.3 | SKendhe@slb.com | 2022-06-30 | 2022-07-20 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC1 Defect Fixing | PY4.0 ¦¦ DATA CONVERSION - DC1 Defect Fixing | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.3 | SKendhe@slb.com | 2022-07-14 | 2022-07-27 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC1 Lessons Learned capture | PY4.0 ¦¦ DATA CONVERSION - DC1 Lessons Learned capture | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.3 | SKendhe@slb.com | 2022-07-28 | 2022-08-10 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC2 Prep | PY4.0 ¦¦ DATA CONVERSION - DC2 Prep | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.3 | SKendhe@slb.com | 2022-08-11 | 2022-08-24 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC2 Execute | PY4.0 ¦¦ DATA CONVERSION - DC2 Execute | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.3 | SKendhe@slb.com | 2022-09-01 | 2022-09-21 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC2 Defect Fixing | PY4.0 ¦¦ DATA CONVERSION - DC2 Defect Fixing | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.4 | SKendhe@slb.com | 2022-09-22 | 2022-10-05 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC2 Lessons Learned capture | PY4.0 ¦¦ DATA CONVERSION - DC2 Lessons Learned capture | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.4 | SKendhe@slb.com | 2022-10-06 | 2022-10-19 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC3 Prep | PY4.0 ¦¦ DATA CONVERSION - DC3 Prep | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.4 | SKendhe@slb.com | 2022-10-06 | 2022-10-19 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC3 Execute | PY4.0 ¦¦ DATA CONVERSION - DC3 Execute | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.4 | SKendhe@slb.com | 2022-10-27 | 2022-11-16 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION -DC3 Defect Fixing | PY4.0 ¦¦ DATA CONVERSION -DC3 Defect Fixing | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.4 | SKendhe@slb.com | 2022-11-17 | 2022-11-30 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC3 Lessons Learned capture | PY4.0 ¦¦ DATA CONVERSION - DC3 Lessons Learned capture | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.4 | SKendhe@slb.com | 2022-11-24 | 2022-12-07 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ END USER TRAINING - Complete End User Training (VILT/ILT) | PY4.0 ¦¦ END USER TRAINING - Complete End User Training (VILT/ILT) | PY4.0 ¦¦ END USER TRAINING | PQ-2022.4 | HSalcedo@slb.com | 2022-10-22 | 2022-11-30 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ END USER TRAINING - Complete End User Training (WBTs) | PY4.0 ¦¦ END USER TRAINING - Complete End User Training (WBTs) | PY4.0 ¦¦ END USER TRAINING | PQ-2022.4 | HSalcedo@slb.com | 2022-10-22 | 2022-11-30 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ END USER TRAINING - Develop Training Strategy | PY4.0 ¦¦ END USER TRAINING - Develop Training Strategy | PY4.0 ¦¦ END USER TRAINING | PQ-2022.3 | HSalcedo@slb.com | 2022-06-02 | 2022-08-10 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ END USER TRAINING - Develop/Finalize Training Materials | PY4.0 ¦¦ END USER TRAINING - Develop/Finalize Training Materials | PY4.0 ¦¦ END USER TRAINING | PQ-2022.4 | HSalcedo@slb.com | 2022-07-14 | 2022-10-05 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ END USER TRAINING -Review Global Template Training Material | PY4.0 ¦¦ END USER TRAINING -Review Global Template Training Material | PY4.0 ¦¦ END USER TRAINING | PQ-2022.4 | HSalcedo@slb.com | 2022-07-14 | 2022-10-05 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ END USER TRAINING - Communicate Training Schedule to End Users | PY4.0 ¦¦ END USER TRAINING - Communicate Training Schedule to End Users | PY4.0 ¦¦ END USER TRAINING | PQ-2022.4 | HSalcedo@slb.com | 2022-10-05 | 2022-11-11 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ GO-LIVE MILESTONE - Business Go-Live | PY4.0 ¦¦ GO-LIVE MILESTONE - Business Go-Live | PY4.0 ¦¦ GO-LIVE MILESTONE | PQ-2023.1 | jbakshi@slb.com | 2023-01-06 | 2023-01-06 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ GOVERNANCE MODEL - Define release scope (business units, enterprise data, current system landscapes) | PY4.0 ¦¦ GOVERNANCE MODEL - Define release scope (business units, enterprise data, current system landscapes) | PY4.0 ¦¦ GOVERNANCE MODEL | PQ-2022.1 | AKulkarni11@slb.com/yileng@slb.com | 2022-01-13 | 2022-03-23 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ LEADERSHIP ACTIONS AND SIGN-OFF - Release Launch with Leadership | PY4.0 ¦¦ LEADERSHIP ACTIONS AND SIGN-OFF - Release Launch with Leadership | PY4.0 ¦¦ LEADERSHIP ACTIONS AND SIGN-OFF | PQ-2022.1 | AKulkarni11@slb.com/yileng@slb.com | 2022-02-10 | 2022-02-23 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ LEADERSHIP ENGAGEMENT - Release Launch with SteerCo | PY4.0 ¦¦ LEADERSHIP ENGAGEMENT - Release Launch with SteerCo | PY4.0 ¦¦ LEADERSHIP ENGAGEMENT | PQ-2022.1 | AKulkarni11@slb.com/yileng@slb.com | 2022-02-17 | 2022-02-17 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ ORGANIZATIONAL READINESS -Identify New Business Roles | PY4.0 ¦¦ ORGANIZATIONAL READINESS -Identify New Business Roles | PY4.0 ¦¦ ORGANIZATIONAL READINESS | PQ-2022.2 | AKulkarni11@slb.com/yileng@slb.com | 2022-02-24 | 2022-06-01 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ ORGANIZATIONAL READINESS - Organization Compliance Review | PY4.0 ¦¦ ORGANIZATIONAL READINESS - Organization Compliance Review | PY4.0 ¦¦ ORGANIZATIONAL READINESS | PQ-2022.3 | HSalcedo@slb.com | 2022-03-10 | 2022-07-27 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Develop PDS Framework | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Develop PDS Framework | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT | PQ-2022.3 | HSalcedo@slb.com | 2022-07-14 | 2022-09-07 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Refine PDS Plan per feedback | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Refine PDS Plan per feedback | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT | PQ-2022.4 | HSalcedo@slb.com | 2022-09-08 | 2022-10-19 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Validate Local Customization of PDS Plan | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Validate Local Customization of PDS Plan | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT | PQ-2022.4 | HSalcedo@slb.com | 2022-10-20 | 2022-11-30 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Mobilize & Train PDS Resources | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Mobilize & Train PDS Resources | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT | PQ-2023.1 | HSalcedo@slb.com | 2022-12-01 | 2023-01-25 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Control Room Planning (Centrally Run) | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Control Room Planning (Centrally Run) | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT | PQ-2022.4 | HSalcedo@slb.com | 2022-10-20 | 2022-11-30 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - PDS support per assigned role (Onsite, Remedy, Control Room) | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - PDS support per assigned role (Onsite, Remedy, Control Room) | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT | PQ-2023.2 | MStewart6@slb.com | 2023-01-12 | 2023-04-19 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Monitor Incident Resolution and Coordinate Actions with Regional Deployment | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Monitor Incident Resolution and Coordinate Actions with Regional Deployment | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT | PQ-2023.2 | HSalcedo@slb.com | 2023-01-26 | 2023-04-05 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Collaborate with Central Team on PDS Plan | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT - Collaborate with Central Team on PDS Plan | PY4.0 ¦¦ POST-DEPLOYMENT SUPPORT | PQ-2022.4 | MStewart6@slb.com | 2022-08-11 | 2022-11-02 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ PROJECT PLAN - Create and publish release plan in ADO, Jira, and Toolbox | PY4.0 ¦¦ PROJECT PLAN - Create and publish release plan in ADO, Jira, and Toolbox | PY4.0 ¦¦ PROJECT PLAN | PQ-2022.1 | JBakshi@slb.com | 2022-01-13 | 2022-03-23 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ PROJECT PLAN - Establish "rough cut" Release Plan on a Page | PY4.0 ¦¦ PROJECT PLAN - Establish "rough cut" Release Plan on a Page | PY4.0 ¦¦ PROJECT PLAN | PQ-2022.1 | JBakshi@slb.com | 2021-12-30 | 2022-03-23 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ PROJECT PLAN - Establish Release Scorecard | PY4.0 ¦¦ PROJECT PLAN - Establish Release Scorecard | PY4.0 ¦¦ PROJECT PLAN | PQ-2022.1 | JBakshi@slb.com | 2021-12-30 | 2022-03-23 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ RESOURCE ASSIGNMENT - ITE Team in Place | PY4.0 ¦¦ RESOURCE ASSIGNMENT - ITE Team in Place | PY4.0 ¦¦ RESOURCE ASSIGNMENT | PQ-2022.1 | AKulkarni11@slb.com/yileng@slb.com | 2022-01-13 | 2022-03-23 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ RESOURCE ASSIGNMENT - Release Managers in Place | PY4.0 ¦¦ RESOURCE ASSIGNMENT - Release Managers in Place | PY4.0 ¦¦ RESOURCE ASSIGNMENT | PQ-2022.1 | AKulkarni11@slb.com/yileng@slb.com | 2021-12-30 | 2022-02-09 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SOLUTION READINESS - SR2 Sprint Reviews and FUT demos Prep | PY4.0 ¦¦ SOLUTION READINESS - SR2 Sprint Reviews and FUT demos Prep | PY4.0 ¦¦ SOLUTION READINESS | PQ-2022.2 | MStewart6@slb.com | 2022-06-16 | 2022-06-29 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SOLUTION READINESS - SR2 Sprint Reviews and FUT demos | PY4.0 ¦¦ SOLUTION READINESS - SR2 Sprint Reviews and FUT demos | PY4.0 ¦¦ SOLUTION READINESS | PQ-2022.3 | MStewart6@slb.com | 2022-06-30 | 2022-07-13 | SAP H2R | ITT SAP | ALL
PY4.0 - MY ¦¦ DESIGN AND BUILD - Solution Build FUT Complete | PY4.0 – MY ¦¦ DESIGN AND BUILD - Solution Build FUT Complete | PY4.0 ¦¦ DESIGN AND BUILD | PQ-2022.2 | MStewart6@slb.com | 2022-06-30 | 2022-06-30 | SAP H2R | ITT SAP | MY
PY4.0 - MY ¦¦ DESIGN AND BUILD - WRI_EF Scope Freeze | PY4.0 – MY ¦¦ DESIGN AND BUILD - WRI_EF Scope Freeze | PY4.0 ¦¦ DESIGN AND BUILD | PQ-2022.3 | MStewart6@slb.com | 2022-09-07 | 2022-09-07 | SAP H2R | ITT SAP | MY
PY4.0 ¦¦ CUTOVER - Cutover Strategy Finalized | PY4.0 ¦¦ CUTOVER - Cutover Strategy Finalized | PY4.0 ¦¦ CUTOVER | PQ-2022.2 | SKendhe@slb.com | 2022-06-06 | 2022-06-06 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - Cutover Plan Finalized | PY4.0 ¦¦ CUTOVER - Cutover Plan Finalized | PY4.0 ¦¦ CUTOVER | PQ-2022.4 | SKendhe@slb.com | 2022-11-03 | 2022-11-16 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - Transport Move to Prod | PY4.0 ¦¦ CUTOVER - Transport Move to Prod | PY4.0 ¦¦ CUTOVER | PQ-2022.4 | SKendhe@slb.com | 2022-12-29 | 2022-12-30 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - MD Transport Move to Prod | PY4.0 ¦¦ CUTOVER - MD Transport Move to Prod | PY4.0 ¦¦ CUTOVER | PQ-2022.4 | SKendhe@slb.com | 2022-12-15 | 2022-12-17 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ CUTOVER - TD Transport Move to Prod | PY4.0 ¦¦ CUTOVER - TD Transport Move to Prod | PY4.0 ¦¦ CUTOVER | PQ-2022.4 | SKendhe@slb.com | 2022-12-29 | 2022-12-29 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - Conversion Scope Freeze | PY4.0 ¦¦ DATA CONVERSION - Conversion Scope Freeze | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.3 | SKendhe@slb.com | 2022-07-27 | 2022-07-27 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC1 Entry | PY4.0 ¦¦ DATA CONVERSION - DC1 Entry | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.2 | SKendhe@slb.com | 2022-06-29 | 2022-06-29 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC1 Exit | PY4.0 ¦¦ DATA CONVERSION - DC1 Exit | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.3 | SKendhe@slb.com | 2022-07-28 | 2022-07-28 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC2 Entry | PY4.0 ¦¦ DATA CONVERSION - DC2 Entry | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.3 | SKendhe@slb.com | 2022-09-01 | 2022-09-01 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC2 Exit | PY4.0 ¦¦ DATA CONVERSION - DC2 Exit | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.3 | SKendhe@slb.com | 2022-09-21 | 2022-09-21 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC3 Entry | PY4.0 ¦¦ DATA CONVERSION - DC3 Entry | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.4 | SKendhe@slb.com | 2022-10-26 | 2022-10-26 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA CONVERSION - DC3 Exit | PY4.0 ¦¦ DATA CONVERSION - DC3 Exit | PY4.0 ¦¦ DATA CONVERSION | PQ-2022.4 | SKendhe@slb.com | 2022-11-17 | 2022-11-17 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ GOVERNANCE MODEL - Go/No-Go Decision | PY4.0 ¦¦ GOVERNANCE MODEL - Go/No-Go Decision | PY4.0 ¦¦ GOVERNANCE MODEL | PQ-2022.4 | AKulkarni11@slb.com/yileng@slb.com | 2022-12-30 | 2022-12-30 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ HAND-OFF TO SUSTAINING - Handoff to sustaining | PY4.0 ¦¦ HAND-OFF TO SUSTAINING - Handoff to sustaining | PY4.0 ¦¦ HAND-OFF TO SUSTAINING | PQ-2023.1 | HSalcedo@slb.com | 2023-03-12 | 2023-03-12 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT1/RT1 Entry | PY4.0 ¦¦ INTEGRATION TESTING - SIT1/RT1 Entry | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.3 | RShinde8@slb.com | 2022-07-28 | 2022-07-28 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT1/RT1 Exit | PY4.0 ¦¦ INTEGRATION TESTING - SIT1/RT1 Exit | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.3 | RShinde8@slb.com | 2022-08-24 | 2022-08-24 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT2/RT2 Entry | PY4.0 ¦¦ INTEGRATION TESTING - SIT2/RT2 Entry | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.3 | RShinde8@slb.com | 2022-09-22 | 2022-09-22 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT2/RT2 Exit | PY4.0 ¦¦ INTEGRATION TESTING - SIT2/RT2 Exit | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.4 | RShinde8@slb.com | 2022-10-19 | 2022-10-19 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ INTEGRATION TESTING - SIT Complete | PY4.0 ¦¦ INTEGRATION TESTING - SIT Complete | PY4.0 ¦¦ INTEGRATION TESTING | PQ-2022.3 | RShinde8@slb.com | 2022-08-24 | 2022-08-24 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ LEADERSHIP ACTIONS AND SIGN-OFF - Release Launch with Leadership Complete | PY4.0 ¦¦ LEADERSHIP ACTIONS AND SIGN-OFF - Release Launch with Leadership Complete | PY4.0 ¦¦ LEADERSHIP ACTIONS AND SIGN-OFF | PQ-2022.1 | AKulkarni11@slb.com/yileng@slb.com | 2022-02-17 | 2022-02-17 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ PROJECT PLAN - Release Plan Published | PY4.0 ¦¦ PROJECT PLAN - Release Plan Published | PY4.0 ¦¦ PROJECT PLAN | PQ-2022.1 | PNagarsheth@slb.com | 2022-01-14 | 2022-01-14 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ RISK MANAGEMENT - Prior Release Risk Consolidation | PY4.0 ¦¦ RISK MANAGEMENT - Prior Release Risk Consolidation | PY4.0 ¦¦ RISK MANAGEMENT | PQ-2022.2 | HSalcedo@slb.com | 2022-02-10 | 2022-04-20 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 1 (Identification) | PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 1 (Identification) | PY4.0 ¦¦ RISK MANAGEMENT | PQ-2022.2 | HSalcedo@slb.com | 2022-04-21 | 2022-06-01 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 2 (Identification) | PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 2 (Identification) | PY4.0 ¦¦ RISK MANAGEMENT | PQ-2022.3 | HSalcedo@slb.com | 2022-06-02 | 2022-07-13 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 3 (Identification & Mitigation) | PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 3 (Identification & Mitigation) | PY4.0 ¦¦ RISK MANAGEMENT | PQ-2022.3 | HSalcedo@slb.com | 2022-07-14 | 2022-08-24 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 4(Mitigation & Action Closure) | PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 4(Mitigation & Action Closure) | PY4.0 ¦¦ RISK MANAGEMENT | PQ-2022.4 | HSalcedo@slb.com | 2022-08-25 | 2022-10-05 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 5 (Mitigation & Action Closure) | PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 5 (Mitigation & Action Closure) | PY4.0 ¦¦ RISK MANAGEMENT | PQ-2022.4 | HSalcedo@slb.com | 2022-10-06 | 2022-11-16 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ RISK MANAGEMENT - Risk Forums | PY4.0 ¦¦ RISK MANAGEMENT - Risk Forums | PY4.0 ¦¦ RISK MANAGEMENT | PQ-2023.1 | HSalcedo@slb.com | 2022-04-21 | 2023-01-27 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 6 (GoLive Decision) | PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 6 (GoLive Decision) | PY4.0 ¦¦ RISK MANAGEMENT | PQ-2022.4 | HSalcedo@slb.com | 2022-11-17 | 2022-12-14 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 7 (Contingency) | PY4.0 ¦¦ RISK MANAGEMENT - Risk Forum 7 (Contingency) | PY4.0 ¦¦ RISK MANAGEMENT | PQ-2023.1 | HSalcedo@slb.com | 2022-12-15 | 2023-01-05 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - Security Build and FUT | PY4.0 ¦¦ SECURITY READINESS - Security Build and FUT | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.3 | KPande@slb.com | 2022-04-07 | 2022-08-10 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS -ecurity Build and FUT - Identify Security Requirements | PY4.0 ¦¦ SECURITY READINESS -ecurity Build and FUT - Identify Security Requirements | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.2 | MAli32@slb.com | 2022-03-10 | 2022-06-15 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS -Security Build and FUT - Security Design Strategy | PY4.0 ¦¦ SECURITY READINESS -Security Build and FUT - Security Design Strategy | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.3 | KPande@slb.com | 2022-04-07 | 2022-08-10 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - Security Build and FUT - Technical Role Build | PY4.0 ¦¦ SECURITY READINESS - Security Build and FUT - Technical Role Build | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.3 | KPande@slb.com | 2022-04-07 | 2022-08-10 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - Security Build and FUT - Security FUT | PY4.0 ¦¦ SECURITY READINESS - Security Build and FUT - Security FUT | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.3 | KPande@slb.com | 2022-04-07 | 2022-08-10 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - DC1 Prep | PY4.0 ¦¦ SECURITY READINESS - DC1 Prep | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.2 | KPande@slb.com | 2022-06-16 | 2022-06-29 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - SIT1/RT1 Prep | PY4.0 ¦¦ SECURITY READINESS - SIT1/RT1 Prep | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.3 | KPande@slb.com | 2022-07-14 | 2022-07-27 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - DC2 Prep | PY4.0 ¦¦ SECURITY READINESS - DC2 Prep | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.3 | KPande@slb.com | 2022-08-11 | 2022-08-24 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - SIT2/RT2 Prep | PY4.0 ¦¦ SECURITY READINESS - SIT2/RT2 Prep | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.3 | KPande@slb.com | 2022-09-08 | 2022-09-21 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - DC3 Prep | PY4.0 ¦¦ SECURITY READINESS - DC3 Prep | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.4 | KPande@slb.com | 2022-10-06 | 2022-10-19 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - SIT3/RT3 Prep | PY4.0 ¦¦ SECURITY READINESS - SIT3/RT3 Prep | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.4 | KPande@slb.com | 2022-11-03 | 2022-11-16 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - Production Cutover Prep | PY4.0 ¦¦ SECURITY READINESS - Production Cutover Prep | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.4 | KPande@slb.com | 2022-11-17 | 2022-12-07 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - User Provisioning | PY4.0 ¦¦ SECURITY READINESS - User Provisioning | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.4 | KPande@slb.com | 2022-10-06 | 2022-12-14 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - User Provisioning - Business Role Setup | PY4.0 ¦¦ SECURITY READINESS - User Provisioning - Business Role Setup | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.4 | KPande@slb.com | 2022-10-06 | 2022-12-14 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - User Provisioning - Production User Setup | PY4.0 ¦¦ SECURITY READINESS - User Provisioning - Production User Setup | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.4 | KPande@slb.com | 2022-10-06 | 2022-12-14 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SECURITY READINESS - User Provisioning - My Access Setup | PY4.0 ¦¦ SECURITY READINESS - User Provisioning - My Access Setup | PY4.0 ¦¦ SECURITY READINESS | PQ-2022.4 | KPande@slb.com | 2022-10-06 | 2022-12-14 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SOLUTION READINESS - SR3 Super User Guided Walkthrough Prep | PY4.0 ¦¦ SOLUTION READINESS - SR3 Super User Guided Walkthrough Prep | PY4.0 ¦¦ SOLUTION READINESS | PQ-2022.3 | MStewart6@slb.com | 2022-07-28 | 2022-08-10 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SOLUTION READINESS - SR3 Super User Guided Walkthrough Support | PY4.0 ¦¦ SOLUTION READINESS - SR3 Super User Guided Walkthrough Support | PY4.0 ¦¦ SOLUTION READINESS | PQ-2022.3 | MStewart6@slb.com | 2022-08-25 | 2022-09-07 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SOLUTION READINESS - Posting Assessment | PY4.0 ¦¦ SOLUTION READINESS - Posting Assessment | PY4.0 ¦¦ SOLUTION READINESS | PQ-2022.2 | MStewart6@slb.com | 2022-01-13 | 2022-06-01 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SOLUTION READINESS - Reporting Assessment | PY4.0 ¦¦ SOLUTION READINESS - Reporting Assessment | PY4.0 ¦¦ SOLUTION READINESS | PQ-2022.2 | MStewart6@slb.com | 2022-01-13 | 2022-06-01 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SOLUTION READINESS - SR1a Fit/Gap Business Signoff | PY4.0 ¦¦ SOLUTION READINESS - SR1a Fit/Gap Business Signoff | PY4.0 ¦¦ SOLUTION READINESS | PQ-2022.2 | MStewart6@slb.com | 2022-06-02 | 2022-06-15 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SOLUTION READINESS - SR1b Localization Business Signoff | PY4.0 ¦¦ SOLUTION READINESS - SR1b Localization Business Signoff | PY4.0 ¦¦ SOLUTION READINESS | PQ-2022.2 | MStewart6@slb.com | 2022-06-02 | 2022-06-15 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SOLUTION READINESS - SR3 Super User Guided Walkthrough Prep | PY4.0 ¦¦ SOLUTION READINESS - SR3 Super User Guided Walkthrough Prep | PY4.0 ¦¦ SOLUTION READINESS | PQ-2022.3 | MStewart6@slb.com | 2022-08-29 | 2022-09-09 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SOLUTION READINESS - Time Element Assessment | PY4.0 ¦¦ SOLUTION READINESS - Time Element Assessment | PY4.0 ¦¦ SOLUTION READINESS | PQ-2022.2 | MStewart6@slb.com | 2022-01-13 | 2022-06-01 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SOLUTION READINESS - Wage Type Assessment | PY4.0 ¦¦ SOLUTION READINESS - Wage Type Assessment | PY4.0 ¦¦ SOLUTION READINESS | PQ-2022.2 | MStewart6@slb.com | 2022-01-13 | 2022-06-01 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SOLUTION READINESS - Master Data Assessment | PY4.0 ¦¦ SOLUTION READINESS - Master Data Assessment | PY4.0 ¦¦ SOLUTION READINESS | PQ-2022.2 | MStewart6@slb.com | 2022-01-13 | 2022-06-01 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SYSTEM INFRASTRUCTURE - SAP/DES DC1 + SIT environment and upgrades complete | PY4.0 ¦¦ SYSTEM INFRASTRUCTURE - SAP/DES DC1 + SIT environment and upgrades complete | PY4.0 ¦¦ SYSTEM INFRASTRUCTURE | PQ-2022.3 | SDas23@slb.com | 2022-06-16 | 2022-07-16 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SYSTEM INFRASTRUCTURE - SAP/DES DC2 + SIT environment and upgrades complete | PY4.0 ¦¦ SYSTEM INFRASTRUCTURE - SAP/DES DC2 + SIT environment and upgrades complete | PY4.0 ¦¦ SYSTEM INFRASTRUCTURE | PQ-2022.3 | SDas23@slb.com | 2022-08-25 | 2022-08-25 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ SYSTEM INFRASTRUCTURE - SAP/DES DC3 + SIT environment and upgrades complete | PY4.0 ¦¦ SYSTEM INFRASTRUCTURE - SAP/DES DC3 + SIT environment and upgrades complete | PY4.0 ¦¦ SYSTEM INFRASTRUCTURE | PQ-2022.4 | SDas23@slb.com | 2022-10-20 | 2022-10-20 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA READINESS - Data Validation Coaching | PY4.0 ¦¦ DATA READINESS - Data Validation Coaching | PY4.0 ¦¦ DATA READINESS | PQ-2022.2 | MStewart6@slb.com | 2022-05-05 | 2022-06-29 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA READINESS - Business Data Validation | PY4.0 ¦¦ DATA READINESS - Business Data Validation | PY4.0 ¦¦ DATA READINESS | PQ-2022.4 | HSalcedo@slb.com | 2022-06-30 | 2022-11-30 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ DATA READINESS - Business Data Validation | PY4.0 ¦¦ DATA READINESS - Business Data Validation | PY4.0 ¦¦ DATA READINESS | PQ-2022.4 | MStewart6@slb.com | 2022-06-16 | 2022-11-30 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ PROJECT VISION AND GOALS - Prepare Release Vision, Value & Goals content | PY4.0 ¦¦ PROJECT VISION AND GOALS - Prepare Release Vision, Value & Goals content | PY4.0 ¦¦ PROJECT VISION AND GOALS | PQ-2022.1 | AKulkarni11@slb.com/yileng@slb.com | 2022-01-13 | 2022-03-23 | SAP H2R | ITT SAP | ALL
PY4.0 ¦¦ STAKEHOLDER MANAGEMENT - Build stakeholder list to manage engagements (PO/PL, SU, Data SMEs) | PY4.0 ¦¦ STAKEHOLDER MANAGEMENT - Build stakeholder list to manage engagements (PO/PL, SU, Data SMEs) | PY4.0 ¦¦ STAKEHOLDER MANAGEMENT | PQ-2022.4 | HSalcedo@slb.com | 2022-03-10 | 2022-11-30 | SAP H2R | ITT SAP | ALL